## Executive Summary & Roadmap
BuildMyWebsiteAI • Master Enhancement Roadmap
Strategic engineering upgrades to transform the platform into an enterprise-grade AI website engine
Total Proposed Features 37 Features Covering AI, Studio, Cloud & Commerce |  | Implementation Phases 5 Phases Organized across 10-week sprint plan |  | Difficulty Mix 14 Easy • 16 Med • 7 Adv Fast high-impact wins available first | Target Capabilities Enterprise SaaS In-browser studio, cloud deploy, payments
Release Schedule & Phased Implementation Plan
Phase | Timeline | Phase Focus & Theme | Key Features Included | Primary Impact & Value
Phase 1 | Weeks 1–2 | Immediate Conversion & Lead Capture | WhatsApp Instant Booking, Web3Forms email contact form, Google Maps iframe embed, Floating call-now bar, Font pairing engine | Turns every generated website into an active, functional sales lead machine for real shop owners without needing a backend server.
Phase 2 | Weeks 3–4 | Interactive In-Browser Studio | Click-to-edit inline text engine, Live hex color wheel picker, Move Up/Down section reordering, Hide/Show section toggles, Custom image uploads | Elevates user experience from a passive preview canvas to an interactive Framer/Wix-style visual editor.
Phase 3 | Weeks 5–6 | AI & Generative Design Diversity | Unsplash HD dynamic photo API, Multi-variant layout shuffling (Bento grids, split hero), AI copywriting tone adjuster, SVG AI logo generator | Solves template repetition completely; guarantees 20,000+ users receive completely unique visual layouts and fresh photography.
Phase 4 | Weeks 7–8 | Zero-Friction Cloud Deployments | 1-click Netlify Deploy API, 1-click Vercel Deploy API, Automated Cloudflare custom domain DNS binding, Auto-generated sitemap & robots.txt | Eliminates manual file unzipping; allows non-technical business owners to launch websites live on the web with a single click.
Phase 5 | Weeks 9–10 | Monetization, Commerce & Scale | Razorpay & Stripe 1-click payment buttons, Menu/catalog pricing table, Token usage quota system, Redis prompt caching, SlowAPI rate limiting | Transforms the academic project into a viable commercial SaaS business capable of handling thousands of concurrent users safely.

## Complete Feature Roadmap
BuildMyWebsiteAI • Feature Backlog & Enhancement Specifications
Detailed technical requirements, implementation steps, complexity metrics, and effort estimates
Feature ID | Category | Feature Name | Detailed Description & Purpose | Implementation Steps & Code Locations | Priority | Difficulty | Est. Effort | Target Phase | Status
FEAT-001 | Lead Capture & Conversion | WhatsApp Click-to-Chat Booking | Directly redirects customers submitting the booking modal to WhatsApp Web/App with pre-filled business inquiry text and phone validation. | In exporter.py handleBookingSubmit: construct wa.me url with country code, business name and service; trigger window.open(waUrl, '_blank'). | Critical | Easy | 4 Hours | Phase 1 | Completed
FEAT-002 | Lead Capture & Conversion | Zero-Backend Contact Email (Web3Forms) | Enables contact forms on exported static websites to dispatch real email notifications to the owner's inbox with zero server dependencies. | In exporter.py contact form: replace alert submit with fetch('https://api.web3forms.com/submit', {method: 'POST', body: formData}). | Critical | Easy | 3 Hours | Phase 1 | Completed
FEAT-003 | Lead Capture & Conversion | Interactive Google Maps Location Embed | Renders an interactive Google Maps iframe pin on the Contact Us page and footer using the business's physical address. | In exporter.py build_page_html for Contact: inject standard Google Maps embed iframe with encodeURIComponent(address). | High | Easy | 2 Hours | Phase 1 | Completed
FEAT-004 | Lead Capture & Conversion | Floating Mobile Sticky CTA Bar | Adds a sleek bottom floating action bar on mobile viewports with 1-click 'Call Now' and 'Book Appointment' buttons. | In style.css: define .mobile-sticky-cta { position: fixed; bottom: 0; } media-queried for max-width 768px with phone/booking triggers. | High | Easy | 3 Hours | Phase 1 | Completed
FEAT-005 | Lead Capture & Conversion | Multi-Service Booking Selection | Allows visitors to select multiple services (checkboxes) and preferred date/time slots in the appointment booking modal dialog. | In modal dialog HTML: replace single service input with multi-select service chips and HTML5 datetime-local picker. | Medium | Medium | 6 Hours | Phase 1 | Completed
FEAT-006 | Lead Capture & Conversion | Automated Booking Confirmation Email | Dispatches an automated email to both the business owner and the customer confirming appointment details. | Backend routes/export.py or Brevo/Resend API integration in webhook receiver. | Medium | Medium | 8 Hours | Phase 2 | Completed
FEAT-007 | Visual Studio & Customization | In-Browser Click-to-Edit Text Engine | Empowers users to click any headline, paragraph, or badge directly in the preview canvas to edit wording in real-time. | In Preview.jsx: add toggle for 'Edit Mode', attach onBlur/onChange to contentEditable elements, update pageTree state in-memory. | Critical | Medium | 12 Hours | Phase 2 | Completed
FEAT-008 | Visual Studio & Customization | Live Hex Color Wheel & Palette Generator | Adds an interactive HTML5 color picker allowing users to customize primary, secondary, and background colors with instant CSS variable updates. | In Preview.jsx toolbar: add color input controls updating document.documentElement.style.setProperty('--primary-color', val). | High | Easy | 4 Hours | Phase 2 | Completed
FEAT-009 | Visual Studio & Customization | Section Reordering (Up/Down Controls) | Provides controls to shift sections up or down (e.g. moving Testimonials above Services or moving FAQ below About Us). | In Preview.jsx: manage section order array in state, render up/down arrow buttons on hover over each section wrapper. | High | Medium | 8 Hours | Phase 2 | Completed
FEAT-010 | Visual Studio & Customization | Section Visibility Toggle (Hide/Show) | Allows users to selectively show or hide specific website sections (e.g. disable FAQ or hide Testimonials if not yet available). | In Preview.jsx & exporter.py: add boolean flags (show_faq, show_testimonials) to page_tree and check before rendering markup. | High | Easy | 4 Hours | Phase 2 | Completed
FEAT-011 | Visual Studio & Customization | Custom Image Upload & Cloudinary CDN | Lets users upload their own custom shop/staff photos instead of relying solely on curated presets. | Frontend file input with preview; backend /upload endpoint saving to Cloudinary / AWS S3 and updating hero_image/gallery URLs. | High | Medium | 10 Hours | Phase 2 | Completed
FEAT-012 | Visual Studio & Customization | Canvas History (Undo / Redo Stack) | Maintains a state stack of user modifications so accidental changes can be reversed with standard Ctrl+Z / Undo button. | In React Context / Preview.jsx: implement past/present/future state array stack for pageTree mutations. | Medium | Medium | 8 Hours | Phase 2 | Completed
FEAT-013 | Visual Studio & Customization | Custom CSS Injection & Code Inspector | Provides advanced users with an embedded code editor modal (Monaco/Ace) to inspect and inject custom CSS rules before export. | Add modal with textarea or Prism.js editor bound to custom_css field in page_tree, appended to style.css on export. | Low | Medium | 6 Hours | Phase 3 | Completed
FEAT-014 | AI & Generative Design | Dynamic Unsplash HD Photo API | Queries the official Unsplash API using business-specific keywords generated by Gemini to inject fresh, authentic royalty-free imagery. | In gemini.py: call Unsplash search API (api.unsplash.com/search/photos?query=...) with business query terms and save HD image URLs. | Critical | Easy | 5 Hours | Phase 3 | Completed
FEAT-015 | AI & Generative Design | Multi-Variant Layout Shuffling Matrix | Ensures 20,000+ users get unique layouts by offering 4+ visual variants per section (Bento grid, Split hero, Minimalist, Full-width). | Create layout variants in exporter.py and React components; assign variant IDs in gemini.py synthesis based on category tone. | Critical | Advanced | 24 Hours | Phase 3 | Completed
FEAT-016 | AI & Generative Design | Category-Driven Google Fonts Pairing Engine | Dynamically pairs complementary Google Fonts based on industry vertical (e.g. Playfair for Luxury Salons, Outfit for Tech Coaching). | In exporter.py & index.html: define font map dict; inject matching Google Fonts <link> tags and update CSS font-family variables. | High | Easy | 4 Hours | Phase 1 | Completed
FEAT-017 | AI & Generative Design | AI Copywriting Tone & Persona Selector | Enables users to choose copywriting tone (Luxurious & Elegant, Friendly & Welcoming, Urgent & Sales-Driven, Professional & Clinical). | In CreationWizardModal.jsx: add tone selector dropdown; inject selected persona instructions into the Gemini master system prompt. | High | Easy | 4 Hours | Phase 3 | Completed
FEAT-018 | AI & Generative Design | AI Blog / Article Generator (3 Pre-written Posts) | Generates 3 full-length, SEO-optimized educational blog articles specific to the business (e.g. 'Top 5 Hair Care Tips' for Salon). | Add Blog page option in multi-page selector; synthesize article schema in gemini.py and export individual blog_[slug].html pages. | Medium | Medium | 14 Hours | Phase 3 | Completed
FEAT-019 | AI & Generative Design | AI SVG Vector Logo Synthesizer | Generates clean, scalable vector SVG brand marks using LLM code generation or Pollinations.ai free image endpoints. | Backend prompt instructing Gemini to output valid inline <svg> with geometric shapes and business initials. | Medium | Medium | 8 Hours | Phase 3 | Completed
FEAT-020 | AI & Generative Design | Multilingual Translation Engine (Hindi/English) | Allows generating the entire website or providing a language switcher toggle in Hindi or regional Indian languages. | Add target_language param in wizard; prompt Gemini to synthesize page_tree values in target language with localized script. | Medium | Medium | 10 Hours | Phase 3 | Planned
FEAT-021 | SEO & Marketing | Dynamic Localized SEO Meta Generator | Automatically generates localized <title> and <meta name='description'> tags targeting local search rankings (e.g. 'Top Salon in Kanpur'). | In gemini.py: prompt AI for seo_title (max 60 chars) and meta_description (max 155 chars); write into <head> of every exported HTML page. | Critical | Easy | 3 Hours | Phase 1 | Planned
FEAT-022 | SEO & Marketing | Open Graph (OG) & Social Card Injection | Embeds og:title, og:image, og:description, and twitter:card tags so WhatsApp and Instagram preview cards look stunning when links are shared. | In exporter.py: inject <meta property='og:...'> tags utilizing the brand name, hero image, and synthesized tagline. | High | Easy | 2 Hours | Phase 1 | Planned
FEAT-023 | SEO & Marketing | Schema.org LocalBusiness JSON-LD Markup | Injects structured data for Google Rich Snippets displaying phone, address, operating hours, and business type directly in search results. | In exporter.py: generate <script type='application/ld+json'> with @type: 'LocalBusiness', name, telephone, and openingHoursSpecification. | High | Easy | 3 Hours | Phase 1 | Planned
FEAT-024 | SEO & Marketing | XML Sitemap & robots.txt Auto-Generation | Bundles valid sitemap.xml and robots.txt files inside every exported ZIP archive to facilitate search engine crawler indexing. | In exporter.py: write sitemap.xml listing all page slugs and robots.txt allowing full crawling with sitemap URL reference. | High | Easy | 2 Hours | Phase 1 | Planned
FEAT-025 | SEO & Marketing | Google Analytics 4 & Meta Pixel Tracking Field | Provides fields in the creation wizard for business owners to input their GA4 Measurement ID (G-XXXXX) or Meta Pixel ID. | In wizard step 3: add optional tracking inputs; inject official gtag.js / pixel tracking snippets into exported HTML header. | Medium | Easy | 3 Hours | Phase 2 | Planned
FEAT-026 | Cloud Deployment & Domains | 1-Click Direct Netlify Deployment API | Allows users to deploy their site live onto Netlify with zero manual unzipping or drag-and-drop, returning a live HTTPS URL in 5 seconds. | Backend integration calling Netlify API (POST https://api.netlify.com/api/v1/sites) with zip payload and storing public URL. | Critical | Medium | 10 Hours | Phase 4 | Planned
FEAT-027 | Cloud Deployment & Domains | 1-Click Vercel Deploy Hook Automation | Connects to Vercel REST API to deploy the project archive directly to production under user or platform teams. | Backend route calling Vercel API (POST /v13/deployments) with file hash payloads. | High | Medium | 12 Hours | Phase 4 | Planned
FEAT-028 | Cloud Deployment & Domains | Cloudflare Custom Domain DNS API | Enables users to connect their own custom domains (e.g. www.mysalon.com) with automated SSL certificate provisioning. | Cloudflare for SaaS integration using Custom Hostnames API to dynamically route user CNAMEs to our multi-tenant proxy. | High | Advanced | 20 Hours | Phase 4 | Planned
FEAT-029 | Cloud Deployment & Domains | GitHub Automated Repo Creation & Push | Automatically creates a private/public GitHub repository on the user's behalf and commits the exported files via Octokit/PyGithub. | FastAPI route using user GitHub OAuth access token to call GitHub REST API /user/repos and commit files in a single tree payload. | Medium | Medium | 10 Hours | Phase 4 | Planned
FEAT-030 | Cloud Deployment & Domains | Instant QR Code Generator for Live Site | Generates and displays a scannable QR code on the success screen so business owners can test the live website instantly on their phone. | Frontend qrcode.react component or Python qrcode library generating base64 PNG in preview and dashboard modals. | High | Easy | 2 Hours | Phase 1 | Planned
FEAT-031 | Commerce & Monetization | Razorpay / Stripe 1-Click Pay Buttons | Embeds instant UPI and Card payment checkout buttons on the Services page so customers can pay advance booking fees. | In wizard: accept Razorpay Key ID; inject Razorpay standard checkout script with configured INR amount and service title. | High | Medium | 8 Hours | Phase 5 | Planned
FEAT-032 | Commerce & Monetization | Digital Menu / Catalog Table Generator | Specialized structured price list / menu block with dietary badges (Veg/Non-Veg), pricing, and descriptions for restaurants and salons. | Create dedicated MenuSection component and corresponding Gemini schema generator for food & service catalogs. | High | Medium | 8 Hours | Phase 3 | Planned
FEAT-033 | Commerce & Monetization | Freemium Credit & Generation Quota System | Provides users with 3 free website generations, requiring credit renewal or subscription for unlimited multi-page exports. | Add credits_balance column in User model; decrement on /generate and /export endpoints; return 402 Payment Required when 0. | Critical | Medium | 8 Hours | Phase 5 | Planned
FEAT-034 | Commerce & Monetization | Razorpay Subscriptions Billing Integration | Integrated payment gateway allowing users to upgrade to Pro / Agency tiers for unlimited exports and custom domain hosting. | FastAPI webhook endpoint handling payment.captured and subscription.charged events, updating user tier in database. | High | Advanced | 16 Hours | Phase 5 | Planned
FEAT-035 | Performance & Security | Redis Prompt Caching for Instant Responses | Caches repeated business prompts and common industry queries in Redis to provide instant (< 1s) responses with zero Gemini API costs. | Wrap Gemini synthesis in Redis get/set cache keyed by MD5 hash of business normalized spec; set TTL to 7 days. | High | Medium | 6 Hours | Phase 5 | Planned
FEAT-036 | Performance & Security | SlowAPI Endpoint Rate Limiting | Implements IP and User rate limiting on generation and auth endpoints to prevent DDoS attacks and Gemini API quota exhaustion. | Add SlowAPI Limiter to FastAPI app: decorate /generate with @limiter.limit('5/minute') and /auth with @limiter.limit('10/minute'). | Critical | Easy | 3 Hours | Phase 1 | Planned
FEAT-037 | Performance & Security | Server-Sent Events (SSE) Streaming Generation | Streams the AI generation steps in real-time over an active SSE connection instead of simulated timing intervals. | FastAPI StreamingResponse yielding progress chunks as Gemini LLM tokens arrive; frontend EventSource updating progress bars. | Medium | Advanced | 14 Hours | Phase 5 | Planned

## Integration Architecture Specs
BuildMyWebsiteAI • Third-Party APIs & Code Snippets
Copy-paste technical specifications and code templates for each external service
Service / API | Primary Purpose | Cost / Tier | API Endpoint & Request Spec | Ready-to-Use Code Snippet
WhatsApp Click-to-Chat | Instant booking lead dispatch to business phone | 100% Free (No API Key Required) | URL Protocol: https://wa.me/[Phone]?text=[Message] | const url = `https://wa.me/91${phone}?text=${encodeURIComponent('Hi! I want to book ' + service)}`; window.open(url, '_blank');
Web3Forms API | Zero-backend email form notifications | 100% Free (250 submissions/mo, no server needed) | POST https://api.web3forms.com/submit Content-Type: application/json | fetch('https://api.web3forms.com/submit', { method: 'POST', headers: {'Content-Type': 'application/json'}, body: JSON.stringify({ access_key: 'YOUR_KEY', name, email, message }) });
Google Maps Embed | Physical location pin without paid Google API key | 100% Free (Zero API Key Required) | Iframe Embed URL: https://maps.google.com/maps?q=[Address]&output=embed | <iframe width="100%" height="300" style="border:0; border-radius:12px;" src={`https://maps.google.com/maps?q=${encodeURIComponent(address)}&output=embed`} />
Unsplash Search API | Dynamic contextual royalty-free HD photography | Free Tier (50 requests/hour free developer key) | GET https://api.unsplash.com/search/photos Authorization: Client-ID [AccessKey] | resp = requests.get('https://api.unsplash.com/search/photos', params={'query': category_term, 'per_page': 5}, headers={'Authorization': f'Client-ID {KEY}'})
Netlify Deploy API | 1-click automated zip file hosting | 100% Free (100GB bandwidth/mo) | POST https://api.netlify.com/api/v1/sites Content-Type: application/zip | resp = requests.post('https://api.netlify.com/api/v1/sites', data=zip_bytes, headers={'Content-Type': 'application/zip', 'Authorization': f'Bearer {NETLIFY_TOKEN}'})
Google Fonts Dynamic Injection | Category-specific typography pairs | 100% Free (Unlimited global CDN) | CDN Link: https://fonts.googleapis.com/css2?family=[Font]:wght@400;700&display=swap | <link rel="preconnect" href="https://fonts.googleapis.com"> <link href="https://fonts.googleapis.com/css2?family=Playfair+Display:wght@700&family=Inter:wght@400;600&display=swap" rel="stylesheet">
Razorpay Standard Checkout | Online advance appointment payments (UPI/Card) | Free setup (2% transaction fee only when paid) | Client Script: https://checkout.razorpay.com/v1/checkout.js | const rzp = new Razorpay({ key: 'rzp_test_xxx', amount: 50000, currency: 'INR', name: brandName, description: 'Appointment Fee' }); rzp.open();